## Timeline
Actual Date | Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
| 2019-06-10 | Fundraising: send stewardship email to past sponsors | Fundraising | Jodie | Jodie | done
| 2019-06-17 | Fundraising: Create Sponsor Form | Fundraising | Jodie | Jodie | done | LGL form
| 2019-06-19 | Fundraising: Review and Update Sponsor Packet | Fundraising | Jodie | Jodie | done | Jodie provided content and TBD created new packet.
| 2019-06-19 | Hotel: Secure room block | Integral Care | Lisa | Lisa | done | Embassy Suites
| 2019-07-01 | Exhibit: Fundraising: Create Exhibitor Registration Form | Fundraising | Jodie | Lady Jane | done; pending review by Jodie | 2 forms created in LGL. One for Credit and Debit cards and the other for Checks and PO payments.
| 2019-07-17 | Design: Present draft announcement flyers | Planning | Annie | Annie | done | Review with Planning Committee on 7/17/19
| 2019-07-19 | Design: incorporate Committee changes of flyers | Integral Care | Lady Jane | Annie | done | Make changes. How do we get approval to print flyers? Ask Ellen. Post on website and create. Update: waiting on Anne to make the changes
| 2019-07-23 | Design: final changes to 2 flyer options | Integral Care | Lady Jane | Annie | done | one has been adopted
| 2019-07-29 | Email: Flyers to all committee members to vote using Forms | Integral Care | Lady Jane | Lisa | done | Lady Jane: update Form with JPEGs (show front/back on one page). Lisa to email link to committe vote. Include due date and change in Forms
| 2019-07-30 | Website: Update Registration Form | Integral Care | Jodie | Lady Jane | forms updated, not live; pending review by Jodie | 2 forms created in LGL. One for Credit and Debit cards and the other for Checks and PO payments.
| 2019-08-01 | Outreach: develop plan to outreach to community | Outreach | Debra | Lady Jane | plan proposed to chair | plan distributed to chair and key members for inputs
| 2019-08-12 | Fundraising: Follow up on sponsor letters (announcing registration opening. Get your name on the site today) | Fundraising | Jodie | Katie |  | follow up emails from letters
| 2019-08-13 | Program: Finalize Call for Papers/Posters Announcement language | Program | Shannon | Lady Jane | done | incorporate changes from Committee
| 2019-08-14 | Fundraising: Follow up with prospective sponsors via email about Registration goes live on 8/26 | Fundraising | Emmitt | Jodie | done
| 2019-08-14 | Outreach: adopt outreach plan | Outreach | Debra | Lady Jane
| 2019-08-15 | CEU: Discuss CEU process w/Learning and Development Team | Integral Care | Jodie | Lady Jane | done | Jessica Pedrick and Aleisha are point persons. Jessica will review all submissions to determine CEU credits. Figure out CEUs for Peers.
| 2019-08-15 | Program: Determine Master of Cermony for Conference | Planning | Willie | Lady Jane | done | Vicky and Kimberly
| 2019-08-21 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie |  | phone calls and emails
| 2019-08-21 | Website: Present updated website with registration links to Committee | Planning | Jodie | Jodie |  | incorporate changes from Committee
| 2019-08-22 | Email: Update Constant Contact lists with 2019 data | Integral Care | Jodie | Jodie |  | from LGL database to CC
| 2019-08-26 | Complete update website with person centered language; nominate section | Communications | Lady Jane | Merri, Anne, Lady Jane
| 2019-08-26 | Email: create Constant Contact email for Registration announcement | Integral Care | Jodie | Jodie
| 2019-08-29 | Email: Registration for 20th CTAAFSC Now Open email announcement | Integral Care | Jodie | Lady Jane |  | Promote all registration, volunteers, exhibitors, sponsors, presenters
| 2019-08-29 | Social: Facebook Boost #1 for Registration | Integral Care | Anne | Chris T. |  | Social to promote keynotes and all registration opportunites
| 2019-08-29 | Website: CTAAFSC Registration Opens | Planning | Jodie | Lady Jane
| 2019-08-29 | Program: Workshops Call for Papers Now Open Announcement including Posters | Program | Shannon | Lady Jane |  | Send to past presenters, academic list, program committee members
| 2019-08-30 | Award/Scholarship: review applications and language | Awards Scholarships | Vicky & Michele | Committee
| 2019-09-02 | Outreach: create prospect list to delivery flyers | Outreach | Debra | Lady Jane
| 2019-09-02 | Outreach: provide Intergal Care emails lists to add for emails | Outreach | Debra | Lady Jane |  | Integral Care can add new names to Constant Contact
| 2019-09-09 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie |  | continue to add to list of prospective sponsors
| 2019-09-16 | Award/Scholarship: Collect potential nominees | Awards Scholarships | Vicky & Michele | Committee |  | add names to spreadsheet for announcement email
| 2019-09-16 | Awards/Scholarship: Update website & links | Awards Scholarships | Integral Care | Jodie |  | based on final copy from Awards Scholarship Committee
| 2019-09-17 | Email: Call for Papers email reminder | Integral Care | Jodie | Lady Jane |  | Send to past presenters, academic list, program committee members
| 2019-09-18 | Outreach: delivery flyers to promote conference | Outreach | Debra | Lady Jane |  | with help from Committee members
| 2019-09-19 | Email: Send 20th CTAAFSC Email Reminder | Integral Care | Anne | Lady Jane |  | Promote all registration, volunteers, exhibitors, sponsors, presenters
| 2019-09-23 | Email: Send email announcing accepting nomininations | Awards Scholarships | Integral Care | Lady Jane
| 2019-09-25 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie |  | continue to add to list of prospective sponsors
| 2019-09-30 | Vendor: Get quote for Golf Cars | Integral Care | Lisa | Lisa |  | Kenfield Golf Car
| 2019-09-30 | Vendor: Get quote from Floral Arrangements | Integral Care | Lisa | Lisa |  | Scott Landry (austinscape.com)
| 2019-10-01 | Email: Past exhibitors to participate | Integral Care | Integral Care | Jodie
| 2019-10-01 | Email: Call for Papers email reminder | Program | Integral Care | Lady Jane
| 2019-10-14 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie |  | continue to add to list of prospective sponsors
| 2019-10-15 | Email: Send 20th CTAAFSC Email Reminder | Integral Care | Jodie | Lady Jane |  | Promote all registration, volunteers, exhibitors, sponsors, presenters
| 2019-10-21 | Email: Call for Papers Reminder - last 10 days | Integral Care | Jodie | TBD
| 2019-10-21 | Social: Social Media for Poster Sessions | Integral Care | Anne | Chris T. |  | Social to promote keynotes and all registration opportunites
| 2019-10-23 | Email: Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
| 2019-11-01 | Volunteer: Update and Finalize Volunteer Sign-Up Sheet | Integral Care | Jodie | Lisa |  | Using LGL
| 2019-11-04 | Volunteer: Discuss Volunteer Roles and Training | Integral Care | Lisa | Jodie |  | Meet w/Lisa to finalize
| 2019-11-04 | Fundraising: Send Prospective sponsorship letters | Integral Care | Emmitt | Jodie |  | continue to add to list of prospective sponsors
| 2019-11-07 | Email: Past exhibitors to participate | Integral Care | Integral Care | Jodie
| 2019-11-13 | Program: Review Call for Papers Application | Program | Shannon | Lady Jane |  | Work with Program Committee. Reviewed in August meeting. Created in LGL in August.
| 2019-11-15 | Program: Call for Papers Closed | Integral Care | Jodie | Jodie
| 2019-11-18 | Email: Send 20th CTAAFSC Email Reminder | Integral Care | Jodie | Lady Jane |  | Promote all registration, volunteers, exhibitors, sponsors, presenters
| 2019-11-18 | Social: Facebook Boost #3 for Registration | Integral Care | Anne | Chris T. |  | Social to promote keynotes and all registration opportunites
| 2019-11-20 | Media: Approve ads for media | Planning | Willie | Anne
| 2019-11-25 | Email: Send Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
| 2019-11-25 | Vendor: Estimate from AV companies | Integral Care | Jodie | Jodie |  | We are looking to use Marco Saucedo, formerly at TMS, waiting on bids from both. Once confirmed, need to secure deposit payment via Lisa
| 2019-11-29 | Vendor: Floral Arrangements Full Payment Due | Integral Care | Jodie | Lisa |  | Emailed Lisa Send Invoice
| 2019-11-29 | Vendor: Golf Cars Full Payment Due to Book | Integral Care | Jodie | Lisa |  | Emailed Lisa to Send Invoice
| 2019-11-29 | Vendor: Request Check to pay for Flowers | Integral Care | Jodie | Lisa
| 2019-12-01 | CEU: Submit CEU paperwork to Learning and Development Team | Integral Care | Katie | Katie |  | Learning and Development Team needs all information pertaining to approved workshops to determine which get CEU approval. They will send back their selections, which will be communicated to committee. Note: this was scheduled for 12/12. We need the list from the Committee in order to move forward.
| 2019-12-01 | Hotel: Coordinate Embassy Suites Room Payments | Integral Care | Lisa | Lisa
| 2019-12-02 | Vendor: Order Ribbons (Presenter, Committee, etc.) | Integral Care | Lisa | Lisa |  | 12/26 Ordered ribbons from Mary Carneiro of Gonzalez Solutions. Rec'd on 1/3/19.
| 2019-12-02 | Program: Select Presenters for Workshop | Program | Shannon | Shannon |  | provide final list to Integral Care to send acceptance letters
| 2019-12-03 | Media: Provide feedback on advertising plan | Planning | Committee | Anne |  | Will create final plan with schedule upon feedback from committee; options sent 12/5, requested feedback by 12/10
| 2019-12-05 | Program: Send approval/decline letters to Call for Papers Applicants | Integral Care | Jodie | Lady Jane
| 2019-12-06 | Website: Update CTAAFSC Website | Integral Care | Jodie | Jodie |  | Add Keynote Speaker Info. Promote awards/scholarships on rotating slide. New target date based on contract delays.
| 2019-12-06 | Program: Request additional information from presenters and co-presenters for program bios and presentation descriptions, if needed Request PPP (on-going request) | Program | Shannon | Anne |  | In years past, we've needed to work with our presenters and co-presenters to ensure consistency throughout the program. Recognizing this is over the holidays, we anticipate delayed responses. Note: this was scheduled to start on 12/12. We need the list from the Committee in order to move forward.
| 2019-12-11 | Email: Send 20th CTAAFSC Email Reminder | Integral Care | Jodie | Lady Jane |  | Promote all registration, volunteers, exhibitors, sponsors, presenters
| 2019-12-11 | Social: Facebook Boost #2 for Registration | Integral Care | Anne | Chris T. |  | Social to promote keynotes and all registration opportunites
| 2019-12-12 | Vendor: Review Levy Catering Menu and make selections | Integral Care | Jodie | Jodie/Kye |  | Email selection and amount to Kery Craig at Levy to get an estimate and then share with Lisa.
| 2019-12-13 | Vendor: Request Check for 2nd Deposit to Palmer | Integral Care | Lisa | Lisa |  | Check mailed on 12/19.
| 2019-12-16 | Vendor: Request 75% payment for Levy | Integral Care | Jodie | Lisa |  | 12/20: Check for $39,375 mailed.
| 2019-12-16 | Volunteer: Request Staff Volunteers | Integral Care | Lisa | Lisa
| 2019-12-18 | Email: Final reminder to nominate Scholarship & Awards | Awards Scholarships | Integral Care | Lady Jane
| 2019-12-18 | Media: Finalize social and paid media plan | Integral Care | Anne | Chris T. |  | Based on Committee's feedback, a draft of the schedule will be shared at the December Planning Meeting. Final schedule provided after media buys
| 2019-12-23 | Award/Scholarship: Close Coleman & Hopkins' Awards | Awards Scholarships | Vicky & Michele | Katie
| 2019-12-24 | Vendor: Levy Catering 75% Payment Due | Integral Care | Lisa | Lisa |  | 12/20: Check for $39,375 mailed.
| 2019-12-27 | Award/Scholarship: provide Committee with nominees received on website | Awards Scholarships | Vicky & Michele | Katie
| 2019-12-31 | Award/Scholarhip: close scholarship nominees | Awards Scholarships | Vicky & Michele | Katie
| 2019-12-31 | Poster: Poster Submissions Closes | Program | Shannon | Lady Jane |  | closed weblink
| 2020-01-02 | Palmer: Submit request for Facilities to move items to Palmer Event Center before conference | Integral Care | Lisa | Lisa |  | 1/2/19: Submitted online request. Same wording as last year.
| 2020-01-02 | Vendor: Menu selections to Levy | Integral Care | Jodie | Lisa |  | Menu selections and function details for all services
| 2020-01-03 | Award/Scholarship: Select Coleman & Hopkins' Awards Recipients | Awards Scholarships | Vicky & Michele | Committee
| 2020-01-03 | Program: Schedule needed photos for Program | Integral Care | Anne | Annie |  | determine photos needed and schedule accordingly
| 2020-01-03 | Posters: Select Poster Presenters | Program | Shannon | Committee
| 2020-01-06 | Award/Scholarship: Select Wood Group, AAMH consumer lodging, Bibby Scholarship, RR Coleman-Callahan lodging | Awards Scholarships | Vicky & Michele | Katie |  | close registration link on website
| 2020-01-06 | Award/Scholarship: Send Coleman & Hopkins' Awards Acceptance Notices | Awards Scholarships | Vicky & Michele | Katie |  | request bios, photos and guests
| 2020-01-06 | Program: Design Conference Program (draft) | Integral Care | Anne | Annie
| 2020-01-06 | Program: Write and edit program content: Conference Welcome Letter by David Presenter Bios and Presentation Summary Awards Bios | Integral Care | Anne | Meri
| 2020-01-06 | Program: Finalize entertainment | Planning | Willie | Committee |  | Is this Planning or Program?
| 2020-01-06 | Posters: Send Poster Acceptance/Decline Notices | Program | Shannon | Lady Jane
| 2020-01-07 | Award/Scholarship: Notify receipents for Wood Group, AAMH consumer lodging, Bibby Lodging, RR Coleman-Callahan lodging | Awards Scholarships | Vicky & Michele | Katie |  | need only names for program. No photos or bios required
| 2020-01-08 | Meet with MCs | Integral Care | Meri | Meri |  | meet to create schedule
| 2020-01-10 | Media: Villager Ad drops | Integral Care | Anne | Anne
| 2020-01-10 | Vendor: Send utility service needs | Integral Care | Jodie | Jodie |  | Email list to Belinda.Nash@austintexas.gov
| 2020-01-11 | Email: Call for Papers FINAL Notice - closes on Friday | Integral Care | Jodie | TBD
| 2020-01-13 | Poster: Final content due from Poster Presenters for Program copy | Integral Care | Shannon | Lady Jane |  | Need. Title and Name of presenters from Charolette (still waiting 1/25)
| 2020-01-13 | Vendor: Request Final payment for Levy | Integral Care | Lisa | Lisa |  | Sent to A/P on Jan 31. Due by Feb 15
| 2020-01-13 | Program: Deliver program outline with most content to Integral Care | Program | Shannon | Anne |  | Include workshop descriptions, all bios
| 2020-01-13 | Program: Deliver two-day schedule for program | Program | Shannon | Anne
| 2020-01-13 | Program: Send reminder to presenters regarding PowerPoints and Handouts | Program | Shannon | Lady Jane |  | Due end of Jan. Email w/requirements and deadlines needs to be created. Sent by Charlotte on 2/4.
| 2020-01-15 | Award/Scholarship: Hopkins and Coleman Awardee bios and photos due for program | Awards Scholarships | Vicky & Michele | Katie |  | program final 1/20/19
| 2020-01-15 | Surveys: (print & on-line) Approve Copy | Planning | Willie | Lady Jane |  | waiting to hear from Leonor, she might handle
| 2020-01-20 | Hotel: Book Lodging for all types of Recipients - scholarships, presenters, awardees | Integral Care | Lisa | Lisa |  | determine who all receives lodging for the various lodging scholarships as well as other requests based on TCDD
| 2020-01-20 | Hotel: Guest Names to Embassy Suites | Integral Care | Lisa | Lisa |  | Due on or before this date.
| 2020-01-20 | Media: Create & Email the Villager Ad | Integral Care | Anne | Annie |  | confirm date to run in paper
| 2020-01-20 | Media: Design ads for media | Integral Care | Anne | Annie
| 2020-01-20 | Print: Name tags: Create and send Name Badges to printer | Integral Care | Jodie | Annie |  | Stuffed and Alpha Order.
| 2020-01-20 | Program: Contact entertainment with contracts | Integral Care | Jodie | Lisa
| 2020-01-20 | Vendor: Order Awards | Integral Care | Lisa | Lisa |  | Get names from committee. Order at Longhorns Awards, sent on 2/8
| 2020-01-20 | Volunteer: Send Volunteer Training Invitation for both days | Integral Care | Lisa | Lisa
| 2020-01-24 | Palmer: Book laptops and projectors from MIS. 6 laptops, 5 projectors, 3 speakers. | Integral Care | Jodie | Lisa |  | 1/2: reserved 4 laptops, 5 projectors. Meri and Katie's laptops can be used. Sent email reminder to MIS re: updating and the speakers
| 2020-01-24 | Vendor: Levy Final Payment Due | Integral Care | Jodie | Lisa
| 2020-01-24 | Volunteer: Send Volunteer Training Reminder 2/11 | Integral Care | Lisa | Lisa |  | reminder
| 2020-01-27 | Email: Exhibitor registration email closes soon | Integral Care |  |  |  | Based on registration numbers and due date for food order to Palmer
| 2020-01-27 | Email: Send FINAL 20th CTAAFSC Email Reminder | Integral Care | Jodie | Lady Jane |  | Registration closing in two days. (may change)
| 2020-01-27 | Fundraising: Finalize names of registrants from Sponsors | Integral Care | Jodie | Lady Jane
| 2020-01-27 | Palmer: Finalize AV Needs | Integral Care | Jodie | Lady Jane
| 2020-01-27 | Print: Proofread CTAAFSC Program | Integral Care | Anne | Anne/Lisa |  | Lisa and Anne will review for typos and share feedback.
| 2020-01-27 | Script: Write script | Integral Care | Meri | Meri |  | Meri writes script, second meeting scheduled after initial meeting with Vicky and Kimberly Was 1/28-25
| 2020-01-27 | Social: Facebook Boost #4 for Registration | Integral Care | Anne | Chris T. |  | Social to promote keynotes and all registration opportunites
| 2020-01-27 | Volunteer: Training #1 | Integral Care | Lisa | Lisa |  | Conference Room 3 Reserved
| 2020-01-27 | Website: Make any program updates to website based on feedback from Program Committee | Integral Care | Anne | Jodie
| 2020-01-28 | Print: Review signage and make list of additional signage needs | Integral Care | Jodie | Lady Jane |  | Be quiet sign for exhibit hall, poster signage
| 2020-01-29 | Palmer: Electricity and table order due to Palmer | Integral Care | Jodie | Lady Jane
| 2020-01-29 | Palmer: Send final count to Palmer for food | Integral Care | Jodie | Lady Jane
| 2020-01-29 | Vendor: Make staples/office depot purchases | Integral Care | Lisa | Lisa |  | Name Badges, Folders
| 2020-01-29 | Program: Approve Program content FINAL | Program | Shannon | Anne
| 2020-01-31 | Script: Send script to MCs | Integral Care | Meri | Meri
| 2020-01-31 | Vendor: Send final A/V needs to Star Perfect | Integral Care | Jodie | Lady Jane
| 2020-01-31 | Volunteer: Reminder to Volunteers #2 | Integral Care | Lisa | Lisa |  | Reminder
| 2020-01-31 | Volunteer: Training #2 | Integral Care | Lisa | Lisa |  | Conference Room 3 Reserved
| 2020-02-03 | Award/Scholarship: Collect Checks & Awards to give to Scholarship recipients | Awards Scholarships | Katie | Lisa
| 2020-02-03 | Email: Exhibitor set up & conference information | Integral Care | Jodie | Jodie
| 2020-02-03 | Fundraising: Send Exhibitor/Sponsors Logistics Email | Integral Care | Jodie | Jodie |  | Provide setup and breakdown info
| 2020-02-03 | Media: Write Media Alert | Integral Care | Anne | Anne |  | Determine release dates
| 2020-02-03 | Palmer: MCOT Availability Discussions | Integral Care | Jodie | Jodie |  | Connect with Marissa to discuss needs and availability.
| 2020-02-03 | Print: Create & duplicate Worksphop packets. CEU forms. Sign-in sheets | Integral Care | Lisa | Lisa
| 2020-02-03 | Print: David Evans signs Certificates | Integral Care | Lisa | Lisa
| 2020-02-03 | Print: Start printing programs | Integral Care | Anne | Annie |  | Everything needs to go to print this day in order to have programs for conference. Orignally 2/12
| 2020-02-03 | Vendor: Request Checks for Entertainment | Integral Care | Lisa | Lisa
| 2020-02-03 | Script: Review script | MCs | Meri | Meri
| 2020-02-04 | Print: Create Playbook | Integral Care | Jodie | Ellen |  | Update last year copy
| 2020-02-04 | Print: large print programs | Integral Care | Anne | Annie |  | 50
| 2020-02-05 | Print: A-Z signs for Registration Boxes | Integral Care | Jodie | Lisa
| 2020-02-05 | Print: Create posters and new signs | Integral Care | Anne | Annie |  | Check what we have and what we need. Silence Please Session in Progress
| 2020-02-05 | Print: Create table cards for sponsors and reserved signs | Integral Care | Jodie | Lisa |  | Use format from last year
| 2020-02-05 | Print: Make poster voting bags | Integral Care | Jodie | Lady Jane
| 2020-02-05 | Print: Names badges returned | Integral Care | Annie | Lisa
| 2020-02-05 | Print: Update Certificates based on participants | Integral Care | Lisa | Lisa
| 2020-02-05 | Program: Send email to speakers with instructions | Integral Care | Jodie | Lady Jane
| 2020-02-05 | Vendor: Connect w/Floral, Golf Car, Entertainment | Integral Care | Jodie | Lisa |  | Discuss logistics of setup, confirm delivery date/time.
| 2020-02-05 | Volunteer: Send Volunteers final email | Integral Care | Lisa | Lisa |  | confirm their volunteer duties and arrival time
| 2020-02-05 | Script: Provide feedback on script | MCs | Meri | Meri
| 2020-02-06 | Email: Send Media Alerts | Integral Care | Anne | Anne |  | Determine release dates
| 2020-02-06 | Print: Alpha Lists for Volunteers to stuff packets | Integral Care | Jodie | Jodie
| 2020-02-06 | Print: Compile list of Attendees for Name Badges | Integral Care | Jodie | Lady Jane |  | Remember to include exhibitors, posters, workshops, students, AISD, and sponsor guests in registration list. Send to Annie once completed.
| 2020-02-06 | Print: In-house name tags | Integral Care | Jodie | Annie |  | Sponsors & Guests, Exihibitors, Presenters, Co-Presenters, Poster, Staff
| 2020-02-06 | Print: Presenter Certificates, Workshop Surveys (CEU and non-CEU), Conference Surveys, Room Guidelines | Integral Care | Jodie | Lisa |  | Internal Printing
| 2020-02-06 | Program: Work on daily run-of-show | Integral Care | Jodie | Jodie
| 2020-02-07 | Exhibit: Update Exhibitor table layout | Integral Care | Jodie | Chris T. |  | Assign booth location
| 2020-02-07 | Palmer: Confirm all A/V needs to Star Perfect | Integral Care | Jodie | Lady Jane
| 2020-02-07 | Palmer: Pick up and laptops, projectors, speakers from MIS | Integral Care | Lisa | Lisa |  | This includes doing updates to the laptops and making sure they connect to wifi. See A/V equipment spreadsheet for needs by room.
| 2020-02-07 | PPT: Compile PowerPoint Loop for Stage | Integral Care | Jodie | Anne |  | Will need updating from last year. Double check sponsors. Comfort Suite
| 2020-02-07 | PPT: Compile PPs of Presenters | Integral Care | Jodie | Anne
| 2020-02-07 | Print: Create Script Book | Integral Care | Jodie | Meri
| 2020-02-07 | Program: Add final program content to website | Integral Care | Anne | Jodie
| 2020-02-07 | Program: Workshops Add PPT to all laptops for workshops | Integral Care | Anne | TBD
| 2020-02-07 | Volunteer: help stuff regisration packets | Integral Care | Lisa | Volunteers |  | Name Badge, Program, etc. Committee to help?
| 2020-02-07 | Volunteer: On-Site Registration Needs | Integral Care | Jodie | Lisa |  | Locate cash box, card swiper, iPad, cash for change, event box
| 2020-02-10 | Email: Send LOGISTICS for All Conference Attendees | Integral Care | Jodie | Lady Jane |  | Presenters, Volunteers, Attendees, etc.
| 2020-02-10 | Palmer: Exhibitor Setup | Integral Care | Chris T. | Chris T. |  | 2-6pm window on Monday
| 2020-02-10 | Palmer: Materials to Palmer Event Center | Integral Care | Lisa | Lisa |  | Coordinate w/ Facilities on delivery time, location, etc.
| 2020-02-10 | Palmer: Organize workshop & CEU sign in sheets, Surveys | Integral Care | Lisa | Lisa
| 2020-02-10 | Print: Final Alpha Lists | Integral Care | Jodie | Lady Jane |  | Registration, Presenters, Volunteers, Posters, Exhibitors
| 2020-02-10 | Print: remaining name tags | Integral Care | Jodie | Annie
| 2020-02-11 | Conference, Day 1 | ALL | ALL | ALL
| 2020-02-11 | Vendor: AV 50% Payment Due to Book | Integral Care | Jodie | Lisa |  | Make final payment day of conference
| 2020-02-12 | Conference, Day 2 | ALL | ALL | ALL
| 2020-02-17 | Surveys: Enter paper surveys | Integral Care | Lisa | Lisa
| 2020-02-28 | Fundraising: Final Program Performance Report (TCDD Grant) | Integral Care | Jodie | Katie
| on-going | Fundraising: Thank you notes to sponsors | Integral Care | Katie | Katie |  | Thank you notes as donations come in

## Awards & Scholarships
Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
2019-08-30 | Award/Scholarship: review applications and language | Awards Scholarships | Vicky & Michele | Committee
2019-09-16 | Award/Scholarship: Collect potential nominees | Awards Scholarships | Vicky & Michele | Committee |  | add names to spreadsheet for announcement email
2019-09-16 | Awards/Scholarship: Update website & links | Awards Scholarships | Integral Care | Jodie |  | based on final copy from Awards Scholarship Committee
2019-09-23 | Email: Send email announcing accepting nomininations | Awards Scholarships | Integral Care | Lady Jane
2019-10-23 | Email: Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
2019-11-25 | Email: Send Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
2019-12-18 | Email: Final reminder to nominate Scholarship & Awards | Awards Scholarships | Integral Care | Lady Jane
2019-12-23 | Award/Scholarship: Close Coleman & Hopkins' Awards | Awards Scholarships | Vicky & Michele | Katie
2019-12-27 | Award/Scholarship: provide Committee with nominees received on website | Awards Scholarships | Vicky & Michele | Katie
2019-12-31 | Award/Scholarhip: close scholarship nominees | Awards Scholarships | Vicky & Michele | Katie
2020-01-03 | Award/Scholarship: Select Coleman & Hopkins' Awards Recipients | Awards Scholarships | Vicky & Michele | Committee
2020-01-06 | Award/Scholarship: Select Wood Group, AAMH consumer lodging, Bibby Scholarship, RR Coleman-Callahan lodging | Awards Scholarships | Vicky & Michele | Katie |  | close registration link on website
2020-01-06 | Award/Scholarship: Send Coleman & Hopkins' Awards Acceptance Notices | Awards Scholarships | Vicky & Michele | Katie |  | request bios, photos and guests
2020-01-07 | Award/Scholarship: Notify receipents for Wood Group, AAMH consumer lodging, Bibby Lodging, RR Coleman-Callahan lodging | Awards Scholarships | Vicky & Michele | Katie |  | need only names for program. No photos or bios required
2020-01-15 | Award/Scholarship: Hopkins and Coleman Awardee bios and photos due for program | Awards Scholarships | Vicky & Michele | Katie |  | program final 1/20/19
2020-02-03 | Award/Scholarship: Collect Checks & Awards to give to Scholarship recipients | Awards Scholarships | Katie | Lisa

## Fundraising
Actual Date | Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
| 2019-06-10 | Fundraising: send stewardship email to past sponsors | Fundraising | Jodie | Jodie | done
| 2019-06-17 | Fundraising: Create Sponsor Form | Fundraising | Jodie | Jodie | done | LGL form
| 2019-06-19 | Fundraising: Review and Update Sponsor Packet | Fundraising | Jodie | Jodie | done | Jodie provided content and TBD created new packet.
| 2019-08-12 | Fundraising: Follow up on sponsor letters (announcing registration opening. Get your name on the site today) | Fundraising | Jodie | Katie |  | follow up emails from letters
| 2019-08-14 | Fundraising: Follow up with prospective sponsors via email about Registration goes live on 8/26 | Fundraising | Emmitt | Jodie | done
| 2019-08-21 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie |  | phone calls and emails
| 2019-09-09 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie |  | continue to add to list of prospective sponsors
| 2019-09-25 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie |  | continue to add to list of prospective sponsors
| 2019-10-14 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie |  | continue to add to list of prospective sponsors
| 2019-11-11 | Fundraising: Follow up with Sponsors regarding registration | Fundraising | Jodie | Jodie
| 2019-12-16 | Fundraising: Follow up with Sponsors regarding registration | Fundraising | Jodie | Jodie
| 2019-01-06 | Fundraising: Follow up with Sponsors regarding registration | Fundraising | Jodie | Jodie |  | final names required for food count

## Program
Actual Date | Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
| 2019-08-13 | Program: Finalize Call for Papers/Posters Announcement language | Program | Shannon | Lady Jane | done | incorporate changes from Committee
| 2019-08-29 | Program: Workshops Call for Papers Now Open Announcement including Posters | Program | Shannon | Lady Jane |  | Send to past presenters, academic list, program committee members
| 2019-10-01 | Email: Call for Papers email reminder | Program | Integral Care | Lady Jane
| 2019-11-13 | Program: Review Call for Papers Application | Program | Shannon | Lady Jane |  | Work with Program Committee. Reviewed in August meeting. Created in LGL in August.
| 2019-12-02 | Program: Select Presenters for Workshop | Program | Shannon | Shannon |  | provide final list to Integral Care to send acceptance letters
| 2019-12-06 | Program: Request additional information from presenters and co-presenters for program bios and presentation descriptions, if needed Request PPP (on-going request) | Program | Shannon | Anne |  | In years past, we've needed to work with our presenters and co-presenters to ensure consistency throughout the program. Recognizing this is over the holidays, we anticipate delayed responses. Note: this was scheduled to start on 12/12. We need the list from the Committee in order to move forward.
| 2019-12-31 | Poster: Poster Submissions Closes | Program | Shannon | Lady Jane |  | closed weblink
| 2020-01-03 | Posters: Select Poster Presenters | Program | Shannon | Committee
| 2020-01-06 | Posters: Send Poster Acceptance/Decline Notices | Program | Shannon | Lady Jane
| 2020-01-13 | Program: Deliver program outline with most content to Integral Care | Program | Shannon | Anne |  | Include workshop descriptions, all bios
| 2020-01-13 | Program: Deliver two-day schedule for program | Program | Shannon | Anne
| 2020-01-13 | Program: Send reminder to presenters regarding PowerPoints and Handouts | Program | Shannon | Lady Jane |  | Due end of Jan. Email w/requirements and deadlines needs to be created. Sent by Charlotte on 2/4.
| 2020-01-29 | Program: Approve Program content FINAL | Program | Shannon | Anne

## Outreach
Actual Date | Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
| 2019-07-01 | Create Exhibitor Registration Form | Outreach | Jodie | Lady Jane |  | 2 forms created in LGL. One for Credit and Debit cards and the other for Checks and PO payments.
| 2019-08-01 | Outreach: develop plan to outreach to community | Outreach | Debra | Lady Jane | plan proposed to chair | plan distributed to chair and key members for inputs
| 2019-08-14 | Outreach: adopt outreach plan | Outreach | Debra | Lady Jane
| 2019-09-02 | Outreach: create prospect list to delivery flyers | Outreach | Debra | Lady Jane
| 2019-09-02 | Outreach: provide Intergal Care emails lists to add for emails | Outreach | Debra | Lady Jane |  | Integral Care can add new names to Constant Contact
| 2019-09-11 | Review and provide ideas for new exhibitors | Outreach | Debra | Lady Jane
| 2019-09-18 | Outreach: delivery flyers to promote conference | Outreach | Debra | Lady Jane |  | with help from Committee members
| 2019-09-20 | Add new exhibtor prospects to Constant Contact | Outreach | Lady Jane | Lady Jane
| 2019-10-16 | Follow up with Exhbitors by committee | Outreach | Debra | Lady Jane |  | send personal emails to contacts to encourage exhibitor registratoin