## Conference Timeline
Actual Date | Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
March | 2020-03-06 | Review 2020 conference evaluations | Integral Care | Lady Jane | Lady Jane/Justin X | Done
| 2020-03-20 | Design artwork for sponsors | Integral Care | Lady Jane | Justin | Done
| 2020-03-24 | Send out thank you artwork to sponsors | Integral Care | Lady Jane | Lady Jane | Postponed due to COVID-19
| 2020-03-27 | Update all LGL forms: registration (4), exhibitor (2), Awards (3), and scholarship (2) | Integral Care | Lady Jane | Lady Jane | Done
| 2020-03-31 | Email: Update Constant Contact lists with 2019 data | Integral Care | Jodie | Lady Jane | Done
April | 2020-04-01 | Fundraising: Thank you notes to sponsors | Integral Care | Jodie | Jodie | Postponed due to COVID-19
| 2020-04-01 | Reach out to Palmer for 2022 dates | Integral Care | Lady Jane | Lisa | Postponed to June
| 2020-04-10 | Design: Present draft announcement flyers | Integral Care | Lady Jane | Justin X | Done
| 2020-04-10 | Fundraising: Create Sponsor Form | Fundraising | Jodie | Jodie | Done
| 2020-04-13 | Fundraising: Review and Update Sponsor Packet | Fundraising | Jodie | Jodie | Postponed
| 2020-04-15 | Complete update website with person centered language; nominate section | Integral Care | Lady Jane | Merri, Anne, Lady Jane | Done
| 2020-04-16 | Email: create Constant Contact email for Registration announcement | Integral Care | Jodie | Jodie | Done
| 2020-04-16 | Email: Call for Papers for 21st Anniversary CTAAFSC Now Open. Email announcement | Integral Care | Jodie | Lady Jane | Done
| 2020-04-16 | Fundraising: send stewardship email to past sponsors | Fundraising | Jodie | Jodie | Postponed due to COVID-19
| 2020-04-16 | Program: Workshops Call for Papers Now Open Announcement including Posters | Program |  | Lady Jane | Done
| 2020-04-16 | Website: CTAAFSC Registration Opens | Program | Jodie | Lady Jane | Postponed to July
| 2020-04-17 | Hotel: Secure room block | Integral Care | Lisa | Lisa | postponed to July
| 2020-04-17 | Social: Facebook Boost #1 for Registration | Integral Care | Justin | Justin X | Postings done, not bosted.
| 2020-04-29 | Outreach: develop plan for outreach to community | Outreach | Lady Jane | Lady Jane | Stick to email, social media
| 2020-04-30 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Jodie | Lady Jane | Done
May | 2020-05-05 | Outreach: create prospect list to deliver flyers | Outreach | Lady Joy | Lady Jane | Building on last year
| 2020-05-06 | Outreach: update email list on Constant Contact | Outreach | Lady Joy | Lady Jane | Done
| 2020-05-12 | Fundraising: Follow up on sponsor letters (announcing registration opening. Get your name on the site today) | Fundraising | Jodie | Jodie | Postponed
| 2020-05-13 | CEU: Discuss CEU process w/Learning and Development Team; Nursing | Integral Care | Lady Jane | Lady Jane | Postponed
| 2020-05-14 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane | Done
| 2020-05-14 | Outreach: adopt outreach plan | Outreach | Lady Joy | Lady Jane | On-going
| 2020-05-19 | Program: Determine Master of Ceremony for Conference | Program | Sonya | Lady Jane | On-going
| 2020-05-20 | Add new exhibitor prospects to Constant Contact | Outreach | Lady Jane | Lady Jane | On-going
| 2020-05-21 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie | Postponed
| 2020-05-28 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
June | 2020-06-01 | Contact Palmer Events Center re: 2022 Conference Dates | Integral Care | Jodie | Lisa
| 2020-06-06 | Call Registrants with duplicate names | Integral Care | Lisa | Lisa
| 2020-06-09 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie
| 2020-06-11 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
| 2020-06-11 | Review and provide ideas for new exhibitors | Outreach | Lady Joy | Lady Jane
| 2020-06-17 | Email: Send 21st CTAAFSC Email Reminder | Integral Care | Lady Jane | Lady Jane
| 2020-06-18 | Outreach: deliver flyers to promote conference | Outreach | Lady Joy | Lady Jane
| 2020-06-25 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
| 2020-06-25 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie
| 2020-06-30 | Vendor: Get quote for Golf Cars | Integral Care | Lisa | Lisa
| 2020-06-30 | Vendor: Get quote from Floral Arrangements | Integral Care | Lisa | Lisa
July | 2020-07-01 | Email: Call for Papers email reminder | Program | Sonya | Lady Jane
| 2020-07-01 | Email: Past exhibitors to participate | Integral Care | Jodie | Lady Jane
| 2020-07-09 | Bi-weekly email in CC | Integral Care | Jodie | Lady Jane
| 2020-07-14 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt | Jodie
| 2020-07-16 | Look for new Exhibitors by committee | Outreach | Lady Joy | Lady Jane
| 2020-07-21 | Email: Call for Papers Reminder - last 10 days | Integral Care | Lady Jane | Lady Jane
| 2020-07-21 | Social: Social Media for Poster Sessions | Integral Care | Lady Jane | Justin X
| 2020-07-23 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Jodie | Lady Jane
| 2020-07-23 | Email: Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
August | 2020-08-06 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
| 2020-08-12 | Fundraising: Send Prospective sponsorship letters | Integral Care | Emmitt | Jodie
| 2020-08-19 | Email: Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
| 2020-08-20 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
September | 2020-09-08 | Start work on papers received | Program Committee | Lady Jane | Lady Jane
| 2020-09-09 | Program: Review Call for Papers Application | Program | Sonya | Lady Jane
| 2020-09-16 | Program: Call for Papers Closed | Integral Care | Lady Jane | Lady Jane
| 2020-09-17 | Email: Send 20th CTAAFSC Email Reminder | Integral Care | Jodie | Lady Jane
| 2020-09-28 | Program: Notify selected workshops | Program | Sonya | Lady Jane
October | 2020-10-01 | Discuss awards and scholarship design | Integral Care | Lady Jane | Justin
| 2020-10-01 | Email all award sponspors about their checks and plaques | Integral care | Lady Jane | Lady Jane
| 2020-10-01 | Poster: Poster Submissions Closes | Program | Sonya | Lady Jane
| 2020-10-07 | Email: Past exhibitors to participate | Integral Care | Integral Care | Jodie
| 2020-10-09 | Reminder: Selected workshoppers and poster presenters to send in their bios (75-word limit for each presenter), final title for the presentation (15 word limit), description of the workshop/ presenter (100 word limit), pictures; keynote speakers 160 word limit | Integral Care | Lady Jane | Lady Jane
| 2020-10-12 | Fundraising: Follow up with Sponsors regarding registration | Fundraising | Jodie | Jodie
| 2020-10-13 | Posters: Select Poster Presenters | Program | Sonya | Committee
| 2020-10-13 | Program: End all things Presenters for Workshop; Program: Send approval/decline letters to Call for Papers Applicants. Notify selected candidates to send their workshop descriptions, bios, pictures by Nov. 25 | Program | Sonya | Lady Jane
| 2020-10-16 | Social: Facebook Boost #3 for Registration | Integral Care | Anne | Justin X
| 2020-10-20 | Email: Send Final Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
| 2020-10-25 | Contact AISD for presentation colors | Integral Care | Jodie | Jodie
| 2020-10-26 | Email: Final reminder to nominate Scholarship & Awards | Awards Scholarships | Integral Care | Lady Jane
November | 2020-11-02 | Volunteer: Update and Finalize Volunteer Sign-Up Sheet | Integral Care | Jodie | Lisa
| 2020-11-03 | Media: Provide feedback on advertising plan | Outreach | Lady Jane | Anne
| 2020-11-06 | Email: Scholarship & Award Nominations close | Awards Scholarships | Integral Care | Lady Jane
| 2020-11-09 | Award/Scholarship: Start sending received awards and scholarship applications to committee members | Awards Scholarships | Vicky Coffee | Lady Jane
| 2020-11-10 | Award/Scholarship: Select Wood Group, AAMH consumer lodging, Bibby Scholarship, RR Coleman-Callahan lodging; Coleman & Hopkins' Awards Recipients | Awards Scholarships | Vicky Coffee | Lady Jane
| 2020-11-11 | Email: Send 20th CTAAFSC Email Reminder | Integral Care | Jodie | Lady Jane
| 2020-11-16 | Email Leonar from AISD - need to get PSS to register | Integral Care | Lady Jane | Lady Jane
| 2020-11-16 | Fundraising: Follow up with Sponsors regarding registration | Fundraising | Jodie | Jodie
| 2020-11-20 | Award/Scholarship: provide Committee with nominees received on website | Awards Scholarships | Vicky Coffee | Lady Jane
| 2020-11-20 | Email: Remind accepted presenters to send in their photos, bios, etc. | Integral Care | Lady Jane | Lady Jane
| 2020-11-25 | Designated presenting times will be finalized | Integral Care | Lady Jane | Lady Jane
| 2020-11-25 | Poster: Final content due from Poster Presenters for Program copy | Integral Care | Sonya | Lady Jane
| 2020-11-26 | Final Deposit and Certificate of Insurance due to Palmer | Integral Care | Jodie | Lisa
| 2020-11-27 | Vendor: Floral Arrangements Full Payment Due | Integral Care | Jodie | Lisa
| 2020-11-30 | Award/Scholarship: Send notification to award winners | Awards Scholarships | Vicky Coffee | Lady Jane
December | 2020-12-01 | CEU: Submit CEU paperwork to Learning and Development Team | Integral Care | Lady Jane | Lady Jane
| 2020-12-03 | Email awards and scholarship donors to send in checks | Integral Care | Lady Jane | Lady Jane
| 2020-12-03 | Vendor: Estimate from AV companies | Integral Care | Jodie | Jodie
| 2020-12-06 | Program: Request additional information from presenters and co-presenters for program bios and presentation descriptions, if needed Request PPP (on-going request) Add to Conference surveys questions: has attendees received any services from Integral Care? | Program | Sonya | Justin
| 2020-12-09 | Program: Finalize entertainment | Program | Lady Jane | Committee
| 2020-12-09 | Social: Facebook Boost #2 for Registration | Integral Care | Anne | Justin X
| 2020-12-09 | Vendor: Review Levy Catering Menu and make selections | Integral Care | Jodie | Jodie/Kye
| 2020-12-10 | Detailed outline of space, event and agenda to Palmer | Integral Care | Jodie | Jodie
| 2020-12-10 | Research name tag options | Integral Care | Anne | Justin
| 2020-12-10 | Vendor: Golf Cars Full Payment Due to Book | Integral Care | Jodie | Lisa
| 2020-12-11 | Volunteer: Discuss Volunteer Roles and Training & OPEN ON WEBSITE | Integral Care | Lisa | Jodie
| 2020-12-14 | Award/Scholarship: Notify recipients for Wood Group, AAMH consumer lodging, Bibby Lodging, RR Coleman-Callahan lodging | Awards Scholarships | Vicky Coffee | Lady Jane
| 2020-12-14 | Email Leonar from AISD - need to provide interpreter | Integral Care | Lady Jane | Lady Jane
| 2020-12-14 | Preliminary outline of events and agenda due to Palmer | Integral Care | Jodie | Jodie
| 2020-12-14 | Vendor: Order Ribbons (Presenter, Committee, etc.) | Integral Care | Lisa | Lisa
| 2020-12-14 | Vendor: Request Check for 2nd Deposit to Palmer | Integral Care | Lisa | Lisa
| 2020-12-14 | Vendor: Request Check to pay for Flowers | Integral Care | Jodie | Lisa
| 2020-12-15 | Submit CEU requirements to Integral Care and Wales | Integral Care | Lady Jane | Lady Jane
| 2020-12-16 | Award/Scholarship: Hopkins and Coleman Awardee bios and photos due for program | Awards Scholarships | Vicky Coffee | Lady Jane
| 2020-12-16 | Email Communication by Hand to reserve ASL interpreters | Integral Care | Lisa | Lisa
| 2020-12-16 | Vendor: Request 75% payment for Levy | Integral Care | Jodie | Lisa
| 2020-12-16 | Volunteer: Request Staff Volunteers | Integral Care | Lisa | Lisa
| 2020-12-17 | Meet with MCs | Integral Care | Meri | Meri
| 2020-12-18 | Media: Approve ads for media | Integral Care | Lady Jane | Anne
| 2020-12-18 | Media: Finalize social and paid media plan | Integral Care | Lady Jane | Justin X
| 2020-12-18 | Program: Deliver program outline with most content to Integral Care | Program | Sonya | Anne
| 2020-12-21 | Design awards and scholarship | Integral Care | Lady Jane | Justin
| 2020-12-21 | Submit check request for florist remaining balance | Integral Care | Lisa | Lisa
| 2020-12-21 | Vendor: Order Awards | Integral Care | Lisa | Lisa
| 2020-12-22 | Program: Deliver two-day schedule for program | Program | Sonya | Anne
| 2020-12-22 | Vendor: Levy Final Payment Due | Integral Care | Jodie | Lisa
| 2020-12-24 | Email: Exhibitor registration email closes soon | Integral Care | Lady Jane | Lady Jane
| 2020-12-28 | Script: Write script | Integral Care | Meri | Meri
| 2020-12-30 | Clean up Registrant Lists (unpaid, dupes) | Integral Care | Jodie/ LJ | Lady Jane
| 2020-12-30 | Email: registration for Conference | Integral Care | Lady Jane | Lady Jane
| 2020-12-31 | Create a Facebook Events depending on number of registered participants | Integral Care | Lady Jane | Lady Jane
| 2020-12-31 | Program: Write and edit program content: Conference Welcome Letter by David Presenter Bios and Presentation Summary Awards Bios | Integral Care | Anne | Meri
| 2020-12-31 | Script: Send script to MCs | Integral Care | Meri | Meri
| 2020-12-31 | Volunteer: Send Volunteer Training Reminders for 1/14 and 1/16 | Integral Care | Lisa | Lisa
| 2021-01-03 | Email Sonya to proofread program for schedule and content | Integral Care | Anne | Jodie
| 2021-01-03 | Send emails to registrants who are unpaid | Integral Care | Lady Jane | Lady Jane
| 2021-01-04 | Final reminder for awards/scholarship checks | Integral Care | Lady Jane | Lisa
| 2021-01-04 | Program: Add 2021 dates to Program and PowerPoint slides | Program | Lady Jane | JXH/Anne
| 2021-01-04 | Program: Schedule needed photos for Program | Integral Care | Anne | JXH
| 2021-01-04 | Submit check requests for Scholarships/Awards | Integral Care | Lady Jane | Lisa
| 2021-01-04 | Vendor: Request Checks for Entertainment | Integral Care | Lisa | Lisa
| 2021-01-06 | Media: Create & Email the Villager Ad | Integral Care | Anne | Justin
| 2021-01-06 | Media: Write Media Alert | Integral Care | Anne | Anne
| 2021-01-06 | Print: Update Certificates based on participants | Integral Care | Sonya | Sonya
| 2021-01-06 | Program: Design Conference Program (draft). Add the logos of our media sponsors and other sponsors to the program. | Integral Care | Anne | JXH
| 2021-01-06 | Request $100 cash to have on hand at conference |  | Lisa | Lisa
| 2021-01-07 | Create excel spreadsheet for nametags | Integral Care | Jodie | Jodie
| 2021-01-07 | Email registrants who need ASL interpreters | Integral Care | Jodie | Jodie
| 2021-01-07 | Hotel: Book Lodging for all types of Recipients - scholarships, presenters, awardees | Integral Care | Lisa | Lisa
| 2021-01-07 | Hotel: Guest Names to Embassy Suites | Integral Care | Lisa | Lisa
| 2021-01-07 | Order Packet envelopes and labels | Integral Care | Lisa | Lisa
| 2021-01-08 | Invoices for entertainers (W9) | Integral Care | Jodie | Lisa
| 2021-01-08 | Meet with MCs | Integral Care | Meri | Meri
| 2021-01-08 | Palmer: Book laptops and projectors from MIS. 6 laptops, 5 projectors, 3 speakers. ***One wireless microphone | Integral Care | Jodie | Lisa
| 2021-01-08 | Palmer: Finalize Electrical Needs | Integral Care | Jodie | Jodie
| 2021-01-08 | Palmer: Submit request for Facilities to move items to Palmer Event Center before conference | Integral Care | Lisa | Lisa
| 2021-01-08 | Print: make decision on ordering more lanyards | Integral Care | Jodie | Jodie
| 2021-01-08 | Print: Proofread CTAAFSC Program | Integral Care | Anne | Anne/Lisa
| 2021-01-08 | Volunteer: Reminder to Volunteers #2 | Integral Care | Lisa | Lisa
| 2021-01-11 | Email: registration for Conference | Integral Care | Lady Jane | Lady Jane
| 2021-01-11 | Finalize exhibitors and sponsors list | Integral Care | Jodie | Lady Jane
| 2021-01-11 | Fundraising: Finalize names of registrants from Sponsors | Integral Care | Jodie | Jodie
| 2021-01-11 | Media: Design ads for media | Integral Care | Anne | Justin
| 2021-01-11 | Media: Villager Ad drops | Integral Care | Anne | Anne
| 2021-01-11 | Palmer: Electricity and table order due to Palmer | Integral Care | Jodie | Jodie
| 2021-01-11 | Print: order lanyards | Integral Care | Justin | Lisa
| 2021-01-11 | Remind Awards & scholarship donors to send in checks in the name of Integral care | Integral Care | Lady Jane | Lady Jane
| 2021-01-11 | Vendor: Make staples/office depot purchases | Integral Care | Lisa | Lisa
| 2021-01-11 | Vendor: Menu selections to Levy | Integral Care | Jodie | Lisa
| 2021-01-11 | Website: Make any program updates to website based on final program | Integral Care | Anne | Justin
| 2021-01-12 | Fundraising: Follow up with Sponsors regarding registration | Fundraising | Jodie | Jodie
| 2021-01-12 | Volunteer: Training #1 | Integral Care | Lisa | Lisa
| 2021-01-13 | Email: registration for Conference | Integral Care | Lady Jane | Lady Jane
| 2021-01-13 | Final surveys to print. Work with Lisa on Workshop Surveys | Integral Care | Lady Jane | Lady Jane
| 2021-01-13 | Palmer: PPT loop for Tuesday & Wednesday program | Integral Care | Lady Jane | Lady Jane
| 2021-01-13 | Program: Approve Program content FINAL | Program | Sonya | Anne
| 2021-01-13 | Program: Send reminder to presenters regarding PowerPoints and Handouts. *** ADD 2022 DATE TO PROGRAM | Program | Sonya | Lady Jane
| 2021-01-13 | Vendor: Request Final payment for Levy | Integral Care | Lisa | Lisa
| 2021-01-14 | Palmer: Security requirements due | Integral Care | Jodie | Jodie
| 2021-01-14 | Print: Send programs to printer | Integral Care | Anne | Justin
| 2021-01-14 | Volunteer: Training #2 | Integral Care | Lisa | Lisa
| 2021-01-15 | Exhibitors: Design passport | Integral Care | Jodie | Chris
| 2021-01-15 | Palmer: Send final food count to Palmer | Integral Care | Jodie | Jodie
| 2021-01-15 | Print Program | Integral Care | Justin/Anne N | Lady Jane
| 2021-01-15 | Print: Review signage and make list of additional signage needs | Integral Care | Jodie | Anne
| 2021-01-15 | Review Palmer digital signage needs | Integral Care | Anne N. | Anne N
| 2021-01-15 | Talk about poster presentation/ competition | Integral Care | Jodie | Lady Jane
| 2021-01-15 | Vendor: Send final A/V needs to Star Perfect | Integral Care | Jodie | Anne
| 2021-01-16 | Social: Facebook Boost #4 for Registration | Integral Care | Anne | Justin X
| 2021-01-18 | Design name tags | Integral Care | Justin | Justin
| 2021-01-18 | Email presenters about microphone costs | Integral Care | Lady Jane | Lady Jane
| 2021-01-18 | Exhibitors: Draft passport | Integral Care | Jodie | Chris
| 2021-01-18 | Print: Review large signage | Integral Care | Anne/Justin | Anne, Jodie, Justin
| 2021-01-19 | Exhibitors: Print and cut exhibitor passports | Integral Care | Chris | Chris
| 2021-01-19 | Program: Work on daily run-of-show | Integral Care | Jodie | Jodie
| 2021-01-20 | Email: Send registered attendees with QR code | Integral Care | Lady Jane | Lady Jane
| 2021-01-20 | Palmer: Send initial count to Palmer for food | Integral Care | Jodie | Jodie
| 2021-01-20 | Print: Compile list of Attendees for Name Badges | Integral Care | Jodie | Lady Jane
| 2021-01-20 | Print: Pick up programs from printer | Integral Care | Anne | Justin
| 2021-01-20 | Review run of show | Integral Care | Jodie | Lady Jane
| 2021-01-21 | Email: registration for Conference | Integral Care | Lady Jane | Lady Jane
| 2021-01-21 | Exhibitors: Email exhibitors about their set up and logistics | Integral Care | Jodie | Chris
| 2021-01-21 | Hotel: Coordinate Embassy Suites Room Payments | Integral Care | Lisa | Lisa
| 2021-01-21 | Palmer: Confirm with Communication by Hand | Integral Care | Jodie | Lisa
| 2021-01-21 | Posters: Make poster voting envelopes | Integral Care | Chris | Chris
| 2021-01-21 | PPT: Compile PowerPoint Loop (for EH2) | Integral Care | Jodie | Lady Jane
| 2021-01-21 | Print: Create and print in-house signage | Integral Care | Lady Jane | Jodie
| 2021-01-21 | Print: Create table cards for sponsors and reserved signs | Integral Care | Jodie | Jodie
| 2021-01-21 | Print: Finish all play book | Integral Care | Lady Jane | Lady Jane
| 2021-01-21 | Print: labels for envelopes (match name badges) | Integral Care | Jodie | Jodie
| 2021-01-21 | Print: Update large signage (if necessary) and send to print | Integral Care | Anne/Justin | Justin
| 2021-01-21 | Print: Update Playbook for 2020 | Integral Care | Jodie | Lady Jane
| 2021-01-21 | Program: Give Linda programs, envelopes and labels for stuffing | Integral Care | Jodie | Lisa
| 2021-01-21 | Program: Send email to speakers with instructions | Integral Care | Lady Jane | Lady Jane
| 2021-01-21 | Program: Start stuffing programs and envelopes | Integral Care | Jodie | Linda
| 2021-01-21 | Script: Provide feedback on script | Integral Care, MCs | Meri | Meri
| 2021-01-21 | Speakers: Overnight $4k Check to Le'Andria | Integral Care | Lisa | Lisa
| 2021-01-21 | Surveys: Create online surveys | Integral Care | Lady Jane | Chris/Lady Jane
| 2021-01-21 | Volunteer: email volunteers to confirm packet stuffing | Integral Care | Lisa | Lisa
| 2021-01-21 | Volunteer: On-Site Registration Needs | Integral Care | Jodie | Lisa
| 2021-01-21 | Volunteer: Send Volunteers final email | Integral Care | Lisa | Lisa
| 2021-01-21 | Y2B: Update Y2B website with map and logistics info | Integral Care | Anne/Ellen | Justin
| 2021-01-22 | Complete day 1 and day 2 to do list with assignments | Integral Care | Jodie | Lady Jane
| 2021-01-22 | Fundraising: Send Sponsors Logistics Email | Integral Care | Jodie | Jodie
| 2021-01-22 | Media: Send media alert | Integral Care | Anne | Anne
| 2021-01-22 | Palmer: Create list and set up Facilities pickup | Integral Care | Lisa/Jodie | Lisa
| 2021-01-22 | Palmer: FINAL PPT loop for Tuesday & Wednesday program | Integral Care | Lady Jane | Lady Jane
| 2021-01-22 | Palmer: Pick up and laptops, projectors, speakers (in Suite 230 closet), clickers (in Chris' cubes) | Integral Care | Lisa | Lisa
| 2021-01-22 | PPT: Add photos and design elements to PPTs for show and loop, put on flash drive | Integral Care | Lady Jane | Justin
| 2021-01-22 | PPT: Compile Presenter's PPTs | Integral Care | Lady Jane | Lady Jane
| 2021-01-22 | Print: Alpha Lists for Volunteers to stuff packets | Integral Care | Jodie | Jodie
| 2021-01-22 | Print: Create & duplicate Workshop packets. CEU forms. Sign-in sheets | Integral Care | Lisa | Lisa
| 2021-01-22 | Print: Create large print programs | Integral Care | Anne | Justin
| 2021-01-22 | Print: David Evans signs Certificates | Integral Care | Sonya | Lisa
| 2021-01-22 | Print: Name tags: Create and send Name Badges to printer | Integral Care | Jodie | Justin
| 2021-01-22 | Print: Pick up Name Badges at Abbey | Integral Care | Justin | Justin
| 2021-01-22 | Print: pickup CT signage from printer | Integral Care | Anne | Justin
| 2021-01-22 | Print: Presenter Certificates, Workshop Surveys (CEU and non-CEU), Conference Surveys, Room Guidelines | Integral Care | Lady Jane | Lisa
| 2021-01-22 | Print: Print and put together play book | Integral Care | Lady Jane | Ellen
| 2021-01-22 | Program: Finish Run of Show | Integral Care | Jodie | Jodie/Anne
| 2021-01-22 | Program: Make shot list for Edwin | Integral Care | Anne | Anne
| 2021-01-22 | Program: Prepare materials for volunteer stuffing | Integral Care | Jodie | Lisa
| 2021-01-22 | Program: rent lens for Edwin? | Integral Care | Anne | Jodie
| 2021-01-22 | Script: Review script | Integral Care, MCs | Meri | Meri
| 2021-01-22 | Staff: Confirm EMCOT plan with Sherry | Integral Care | Anne | Anne
| 2021-01-22 | Surveys: Create and print table cards with URL for surveys | Integral Care | Lady Jane | Chris
| 2021-01-22 | Surveys: Create survey URLs | Integral Care | Lady Jane | Justin
| 2021-01-22 | Surveys: Draft Day #1 and 2 emails for online surveys | Integral Care | Lady Jane | Chris
| 2021-01-22 | Vendor: Connect w/Floral, Golf Car, Entertainment | Integral Care | Jodie | Lisa
| 2021-01-22 | Volunteer: prepare materials for volunteers | Integral Care | Lisa | Lisa
| 2021-01-25 | Exhibitors: Send follow-up logistics email to exhibitors | Integral Care | Jodie | Chris
| 2021-01-25 | Media: Call select media | Integral Care | Anne | Anne
| 2021-01-25 | Palmer: Collect chairs for Rep. Coleman | Integral Care | Lisa | Lady Jane
| 2021-01-25 | Palmer: Confirm all A/V needs to Star Perfect | Integral Care | Jodie | Jodie
| 2021-01-25 | Print: Create Script Book | Integral Care | Meri | Meri
| 2021-01-25 | Print: Finalize Awards/Scholarships put in Frames | Integral Care | Lady Jane | Lady Jane/Justin
| 2021-01-25 | Print: new envelope labels & name badge labels for new registrants since 1/15 | Integral Care | Lady Jane | Lady Jane
| 2021-01-25 | Print: Print and put together Run of Shows | Integral Care | Jodie | Jodie
| 2021-01-25 | Print: print large print programs (in-house) | Integral Care | Anne | Justin
| 2021-01-25 | Program: Load PPTs of Presenters to laptops | Integral Care | Lady Jane | Justin
| 2021-01-25 | Program: Send shot list for Edwin, call to review | Integral Care | Anne | Anne
| 2021-01-25 | Surveys: Schedule Day #1 and 2 emails for online surveys in Constant Contact | Integral Care | Lady Jane | Chris
| 2021-01-25 | Volunteer: help stuff registration packets | Integral Care | Lisa | Volunteers
| 2021-02-01 | Email: Send LOGISTICS for All Conference Attendees | Integral Care | Jodie | Lady Jane
| 2021-02-01 | Email: Send LOGISTICS for All workshop presenter Attendees, awardees, guests, program | Integral Care | Jodie | Lady Jane
| 2021-02-01 | Media: Re-send media alert | Integral Care | Anne | Anne
| 2021-02-01 | Palmer: Decorate green room | Integral Care | Lady Jane | Lady Jane
| 2021-02-01 | Palmer: Exhibitor Setup | Integral Care | Chris | Chris
| 2021-02-01 | Palmer: Materials to Palmer Event Center | Integral Care | Lisa | Lisa
| 2021-02-01 | Palmer: Organize workshop & CEU sign in sheets, Surveys | Integral Care | Lisa | Lisa
| 2021-02-01 | Palmer: Set up laptops in meeting rooms, test PPTs and clickers | Integral Care | Justin | Justin
| 2021-02-01 | Print: A-Z signs for Registration Boxes | Integral Care | Jodie | Ellen
| 2021-02-01 | Print: Final Alpha Lists | Integral Care | Jodie | Jodie
| 2021-02-01 | Print: In-house labels for Name Badges | Integral Care | Jodie | Lady Jane
| 2021-02-01 | Print: In-house labels for Name Badges | Integral Care | Jodie | Lady Jane
| 2021-02-01 | Print: labels for envelopes (new name badges) | Integral Care | Jodie | Jodie
| 2021-02-01 | Vendor: AV 50% Payment Due to Book | Integral Care | Jodie | Lisa
| 2021-02-01 | Website: Update CTAAFSC Website - close registration at 7am | Integral Care | Jodie | Justin
| 2021-02-02 | Conference, Day 1 | ALL | ALL | ALL
| 2021-02-03 | Conference, Day 2 | ALL | ALL | ALL
| 2021-02-17 | Surveys: Enter paper surveys | Integral Care | Lisa | Lisa
| 2021-02-24 | Fundraising: Final Program Performance Report (TCDD Grant) | Integral Care | Jodie | Katie
| 2021-02-24 | Work on CEUs for nurses and other requests | Integral Care | Jodie | Lady Jane
| 2021-11-22 | Notify award winners | Integral Care | Lady Jane | Lady Jane
| 2021-12-10 | Draft surveys copy. General and Workshop surveys | Integral Care | Lady Jane | Lady Jane
| 21/21/2021 | Posters: Raffle tickets to put in packets for poster competition voting | Integral Care | Lady Jane | Lisa

## Awards & Scholarships
Actual Date | Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
| 2020-04-16 | Program: Workshops Call for Papers Now Open Announcement including Posters | Program | Jodie | Lady Jane
| 2020-07-23 | Email: Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
| 2020-08-19 | Email: Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
| 2020-10-20 | Email: Send Final Reminder Scholarship & Award Nominations | Awards Scholarships | Integral Care | Lady Jane
| 2020-10-26 | Email: Final reminder to nominate Scholarship & Awards | Awards Scholarships | Integral Care | Lady Jane
| 2020-11-06 | Email: Scholarship & Award Nominations close | Awards Scholarships | Integral Care | Lady Jane
| 2020-11-09 | Award/Scholarship: Start sending received awards and scholarship applications to committee members | Awards Scholarships | Vicky Coffee | Lady Jane
| 2020-11-10 | Award/Scholarship: Select Wood Group, AAMH consumer lodging, Bibby Scholarship, RR Coleman-Callahan lodging; Coleman & Hopkins' Awards Recipients | Awards Scholarships | Vicky Coffee | Lady Jane |  | close registration link on website
| 2020-11-20 | Award/Scholarship: provide Committee with nominees received on website | Awards Scholarships | Vicky & Michele | Lady Jane
| 2020-11-30 | Award/Scholarship: Send notification to award winners | Awards Scholarships | Vicky Coffee | Lady Jane |  | request bios, photos for Awards. request w9 for scholarships request guests for Awards and Scholarships. ideally 2 per recipient
| 2020-12-14 | Award/Scholarship: Notify recipients for Wood Group, AAMH consumer lodging, Bibby Lodging, RR Coleman-Callahan lodging | Awards Scholarships | Vicky Coffee | Lady Jane |  | need only names for program. No photos or bios required
| 2020-12-16 | Award/Scholarship: Hopkins and Coleman Awardee bios and photos due for program | Awards Scholarships | Vicky Coffee | Lady Jane |  | program final 1/20/19
| 2021-02-02 | Conference, Day 1 | ALL | ALL | ALL
| 2021-02-03 | Conference, Day 2 | ALL | ALL | ALL

## Fundraising
Actual Date | Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
| 2020-04-10 | Fundraising: Create Sponsor Form | Fundraising | Jodie | Jodie
| 2020-04-13 | Fundraising: Review and Update Sponsor Packet | Fundraising | Jodie | Jodie
| 2020-04-16 | Email: Call for Papers, application for awards, exhibitors for 2021 Now Open. Email announcement | Integral Care | Jodie | Lady Jane
| 2020-04-16 | Fundraising: send stewardship email to past sponsors | Fundraising | Jodie | Jodie
| 2020-05-12 | Fundraising: Follow up on sponsor letters (announcing registration opening. Get your name on the site today) | Fundraising | Jodie | Jodie
| 2020-05-21 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt Hayes | Jodie
| 2020-06-09 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt Hayes | Jodie
| 2020-06-25 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt Hayes | Jodie
| 2020-07-14 | Fundraising: Follow up with prospective sponsors | Fundraising | Emmitt Hayes | Jodie
| 2020-10-12 | Fundraising: Follow up with Sponsors regarding registration | Fundraising | Jodie | Jodie
| 2020-11-16 | Fundraising: Follow up with Sponsors regarding registration | Fundraising | Jodie | Jodie
| 2021-01-12 | Fundraising: Follow up with Sponsors regarding registration | Fundraising | Jodie | Jodie
| 2021-02-02 | Conference, Day 1 | ALL | ALL | ALL
| 2021-02-03 | Conference, Day 2 | ALL | ALL | ALL

## Program
Actual Date | Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
| 2020-04-16 | Program: Workshops Call for Papers Now Open Announcement including Posters | Program | Jodie | Lady Jane
| 2020-04-16 | Website: CTAAFSC Registration Opens | Program | Jodie | Lady Jane
| 2020-05-19 | Program: Determine Master of Ceremony for Conference | Program | Sonya Hosey | Lady Jane
July | 2020-07-01 | Email: Call for Papers email reminder | Program | Sonya Hosey | Lady Jane
| 2020-12-18 | Program: Deliver program outline with most content to Integral Care | Program | Sonya Hosey | Anne
| 2020-12-22 | Program: Deliver two-day schedule for program | Program | Sonya Hosey | Anne
| 2021-01-04 | Program: Add 2021 dates to Program and PowerPoint slides | Program | Lady Jane | JXH/Anne
| 2021-01-13 | Program: Approve Program content FINAL | Program | Sonya Hosey | Anne
| 2021-01-13 | Program: Send reminder to presenters regarding PowerPoints and Handouts. *** ADD 2021 DATE TO PROGRAM | Program | Sonya Hosey | Lady Jane
September | 2020-09-08 | Start work on papers received | Program Committee | Lady Jane | Lady Jane
| 2020-09-09 | Program: Review Call for Papers Application | Program | Sonya Hosey | Lady Jane
| 2020-09-16 | Program: Call for Papers Closed | Integral Care | Lady Jane | Lady Jane
| 2020-09-28 | Program: Notify selected workshops | Program | Sonya Hosey | Lady Jane
| 2020-10-01 | Poster: Poster Submissions Closes | Program | Sonya Hosey | Lady Jane
| 2020-10-13 | Posters: Select Poster Presenters | Program | Sonya Hosey | Committee
| 2020-10-13 | Program: End all things Presenters for Workshop; Program: Send approval/decline letters to Call for Papers Applicants. Notify selected candidates to send their workshop descriptions, bios, pictures by Nov. 25 | Program | Sonya Hosey | Sonya
| 2020-12-06 | Program: Request additional information from presenters and co-presenters for program bios and presentation descriptions, if needed Request PPP (on-going request) Add to Conference surveys questions: has attendees received any services from Integral Care? | Program | Sonya Hosey | Justin
| 2020-12-09 | Program: Finalize entertainment | Program | Lady Jane | Committee
| 2020-12-18 | Program: Deliver program outline with most content to Integral Care | Program | Sonya Hosey | Anne
| 2020-12-22 | Program: Deliver two-day schedule for program | Program | Sonya Hosey | Anne
| 2021-02-02 | Conference, Day 1 | ALL | ALL | ALL
| 2021-02-03 | Conference, Day 2 | ALL | ALL | ALL

## Outreach
Actual Date | Target Date | Description | Committee | Project Manager | Implementer | Status | Notes
April | 2020-04-16 | Email: Call for Papers, application for awards, exhibitors for 2021 CTAAFSC Now Open. Email announcement | Integral Care | Jodie | Lady Jane
| 2020-04-30 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
May | 2020-05-05 | Outreach: create prospect list to deliver flyers | Outreach | Lady Joy | Lady Jane
| 2020-05-06 | Outreach: update email list on Constant Contact | Outreach | Lady Joy | Lady Jane
| 2020-05-14 | Bi-weekly email in CC, updates on COVID-19, | Outreach | Lady Jane | Lady Jane
| 2020-05-14 | Outreach: adopt outreach plan | Outreach | Lady Joy | Lady Jane
| 2020-05-20 | Add new exhibitor prospects to Constant Contact | Outreach | Lady Jane | Lady Jane
| 2020-05-28 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
| 2020-06-11 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
| 2020-06-11 | Review and provide ideas for new exhibitors | Outreach | Lady Joy | Lady Jane
| 2020-06-18 | Outreach: deliver flyers to promote conference | Outreach | Lady Joy | Lady Jane
| 2020-06-25 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
| 2020-07-09 | Bi-weekly email in CC | Outreach | Jodie | Lady Jane
| 2020-07-16 | Look for new Exhibitors by committee | Outreach | Lady Joy | Lady Jane
| 2020-07-23 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Jodie | Lady Jane
August | 2020-08-06 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
| 2020-08-20 | Bi-weekly email in CC, updates on COVID-19, CT | Outreach | Lady Jane | Lady Jane
| 2020-11-03 | Media: Provide feedback on advertising plan | Outreach | Lady Jane | Anne
| 2021-02-02 | Conference, Day 1 | ALL | ALL | ALL
| 2021-02-03 | Conference, Day 2 | ALL | ALL | ALL